## Basic Manual Gantt Chart
Task Name	Start Date	End Date	Duration		Start Date in Number Form	42887.00		Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
Program of the components with arduino leonardo	6/1/2017	6/8/2017	7
Desing the PCB :Thermistor, heater, driver for the motor	6/3/2017	6/9/2017	6
Produce final PCB	6/9/2017	6/12/2017	3
3D design: handle	6/2/2017	6/5/2017	3
3D printig: handle	6/5/2017	6/7/2017	2
Frame laser cut	6/10/2017	6/11/2017	1
Program with thermistor as a imput to control the hearter	6/9/2017	6/12/2017	3
Programing for the PCB	6/10/2017	6/13/2017	3
Sistem integration	6/12/2017	6/14/2017	2
Document everything	6/1/2017	6/16/2017	15
Video + slide	6/14/2017	6/16/2017	2

					Key:	Calculated Cell					Manual Entry Cell
						These cells will be automatically calculated based on the inputs on other cells.					These cells require manual input so the calculated cells have data to work with.

## Gantt Chart - Manual End Date
Task Name	Start Date	End Date	Duration (Days)	Days Complete	Days Remaining	Percent Complete		Start Date in Number Form	42911.00		Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
Task One	6/25/2017	7/30/2017	35	17.50	17.50	50%
Task Two	6/26/2017	7/31/2017	35	26.25	8.75	75%
Task Three	6/27/2017	8/1/2017	35	8.75	26.25	25%
Task Four	6/28/2017	8/2/2017	35	35.00	0.00	100%
Task Five	6/29/2017	8/3/2017	35	26.25	8.75	75%
Task Six	6/30/2017	8/4/2017	35	12.25	22.75	35%
Task Seven	7/1/2017	8/5/2017	35	8.75	26.25	25%
Task Eight	7/2/2017	8/6/2017	35	24.50	10.50	70%
Task Nine	7/3/2017	8/7/2017	35	5.25	29.75	15%
Task Ten	7/4/2017	8/8/2017	35	21.00	14.00	60%
Task Eleven	7/5/2017	8/9/2017	35	22.75	12.25	65%
Task Twelve	7/6/2017	8/10/2017	35	8.75	26.25	25%
Task Thirteen	7/7/2017	8/11/2017	35	10.50	24.50	30%
Task Fourteen	7/8/2017	8/12/2017	35	17.50	17.50	50%
Task Fifteen	7/9/2017	8/13/2017	35	14.00	21.00	40%
Task Sixteen	7/10/2017	8/14/2017	35	12.25	22.75	35%
Task Seventeen	7/11/2017	8/15/2017	35	5.25	29.75	15%

								Key:	Calculated Cell					Manual Entry Cell
									These cells will be automatically calculated based on the inputs on other cells.					These cells require manual input so the calculated cells have data to work with.

## Gantt Chart - Manual Duration
Task Name	Start Date	End Date	Duration (Days)	Days Complete	Days Remaining	Percent Complete		Start Date in Number Form	42576.00		Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
Task One	7/25/2016	7/30/2016	5	2.50	2.50	50%
Task Two	7/27/2016	8/1/2016	5	3.75	1.25	75%
Task Three	7/27/2016	8/4/2016	8	2.00	6.00	25%
Task Four	7/29/2016	8/6/2016	8	8.00	0.00	100%
Task Five	8/1/2016	8/9/2016	8	6.00	2.00	75%
Task Six	8/1/2016	8/5/2016	4	1.40	2.60	35%
Task Seven	8/3/2016	8/10/2016	7	1.75	5.25	25%
Task Eight	8/5/2016	8/12/2016	7	4.90	2.10	70%
Task Nine	8/3/2016	8/9/2016	6	0.90	5.10	15%
Task Ten	8/6/2016	8/10/2016	4	2.40	1.60	60%
Task Eleven	8/7/2016	8/13/2016	6	3.90	2.10	65%
Task Twelve	8/10/2016	8/16/2016	6	1.50	4.50	25%
Task Thirteen	8/14/2016	8/19/2016	5	1.50	3.50	30%
Task Fourteen	8/15/2016	8/23/2016	8	4.00	4.00	50%
Task Fifteen	8/16/2016	8/26/2016	10	4.00	6.00	40%
Task Sixteen	8/17/2016	8/28/2016	11	3.85	7.15	35%
Task Seventeen	8/18/2016	8/29/2016	11	1.65	9.35	15%

								Key:	Calculated Cell					Manual Entry Cell
									These cells will be automatically calculated based on the inputs on other cells.					These cells require manual input so the calculated cells have data to work with.