## Project Planner
Final Project Plan
| Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
Sr.NO | ACTIVITY | PLAN START | PLAN DURATION (Days) | ACTUAL START | ACTUAL DURATION (Days) | PERIODS
[6 empty] | 2017-01-25 | 2017-01-31 | 2017-02-01 | 2017-02-07 | 2017-02-08 | 2017-02-10 | 2017-03-29 | 2017-04-04 | 2017-04-26 | 2017-04-28 | 2017-04-29 | 2017-05-02 | 2017-05-04 | 2017-05-24 | 2017-05-30 | 2017-05-31 | 2017-06-01 | 2017-06-06 | 2017-06-07 | 2017-06-10 | 2017-06-11 | 2017-06-12 | 2017-06-13 | 2017-06-14 | 2017-06-15 | 2017-06-16 | 2017-11-12
1 | Decide potential final project | 2017-01-25 | 7 | 2017-01-25 | 6
2 | Finalize the block diagram & methods/electronics needed for project | 2017-02-01 | 7 | 2017-02-01 | 5
3 | Study the working of ultrasonic transreceivers | 2017-02-08 | 3 | 2017-02-08 | 3
4 | Prepare circuit and board to drive motors | 2017-03-29 | 7 | 2017-03-29 | 6
5 | Study and make circuit diagram for transmitter and receiver | 2017-04-26 | 3 | 2017-04-26 | 3
6 | Prepare transmitter and receiver boards and test them | 2017-04-29 | 4 | 2017-04-29 | 3
7 | Prepare algorithm and write code in embedded C & test it | 2017-05-24 | 7 | 2017-05-24 | 6
8 | Design the mechanical structure for base of suitcase in solidworks | 2017-05-31 | 7 | 2017-05-31 | 6
9 | 3D print all required parts & assemble the structure | 2017-06-07 | 4 | 2017-06-07 | 3
10 | Make suitcase using foam | 2017-06-11 | 2 | 2017-06-11 | 2
11 | Design boxes for transmitter, receiver & main conrol board | 2017-06-13 | 1 | 2017-06-13 | 1
12 | 3D print the boxes | 2017-06-14 | 2 | 2017-06-14 | 2
13 | Assemble the suitcase and test the working | 2017-06-15 | 1 | 2017-06-15 | 1
14 | Make final project slide & video | 2017-06-16 | 1 | 2017-06-16 | 1
15 | Make handle for suitcase by milling the foam | 2017-11-12 | 1 | 2017-11-12 | 1